## SummaryTables
Status | Pass
Row Labels | Count of ID
Core Game Flow | 27
Deployment and Platform Behaviour | 4
Internal Logic | 6
Player Interaction Systems | 24
Rendering, UI, and Audio | 10
Grand Total | 71
Row Labels | Count of ID
Pass | 71
Grand Total | 71

## TestCases
ID | Feature | Technique | Module / Subsystem | Group | Partition / case class | Steps | Expected result | Status | Test Date | Notes | Status Input (DO NOT TOUCH)
BT01 | Initial load | Black-box | Deployment & Launch | Deployment and Platform Behaviour | Execution context: Live Server | 1. Open the game in Live Server. 2. Wait for loading to finish. | Start screen appears; no black screen; no critical console errors. | Pass | 2026-03-17 | - | Pass
BT02 | Start screen assets | Black-box | Start / Mode Selection | Core Game Flow | Start state / visible assets | 1. Open the game. 2. Observe the start screen. | Background, title, text, fonts, and menu elements are visible and aligned. | Pass | 2026-03-17 | - | Blocked
BT03 | Start screen input | Black-box | Start / Mode Selection | Core Game Flow | Enter key in start state | 1. Open the start screen. 2. Press Enter. | The correct transition to the next state happens. | Pass | 2026-03-17 | - | Not Tested
BT04 | Intro progression | Boundary Value | Tutorial / Story Flow | Core Game Flow | Enter key in intro state | 1. Reach the intro. 2. Press Enter once 3. Press Enter again. | First press completes or speeds up the text; second press enters gameplay. | Pass | 2026-03-17 | - | Fail
BT05 | Gameplay render | Black-box | Rendering / UI | Rendering, UI, and Audio | Playing state render | 1. Start the game. 2. Observe the main canvas. | Gameplay is visible; map renders; canvas is not black. | Pass | 2026-03-17 | -
BT06 | Movement input | Black-box | Player Controls & Camera | Player Interaction Systems | Valid movement input | 1. Enter gameplay. 2. Use movement keys. | Player movement responds correctly; no unexpected input lock. | Pass | 2026-03-17 | -
BT07 | Win condition | Black-box | Core Outcomes | Core Game Flow | Win state | 1. Play until the win condition is met. | Win screen appears correctly and the game does not crash. | Pass | 2026-04-15 | Working correctly for both story and normal mode
BT08 | Normal-mode final objective | Black-box | Doors / Objectives | Player Interaction Systems | map1 / map2 / map3 | 1. From Start choose NORMAL MODE; 2. Load each difficulty option; 3. Reach the final objective for each map. | Each normal-mode map reaches the win screen without soft-locking. | Pass | 2026-04-16 | Split execution by all three maps rather than treating win flow as one generic case.
BT09 | Lose condition | Black-box | Core Outcomes | Core Game Flow | Lose state | 1. Play until the lose condition is met. | Lose screen appears correctly and the game does not crash. | Pass | 2026-03-17 | -
BT10 | Restart / return flow | Black-box | Core Outcomes | Core Game Flow | End-state restart / return | 1. Reach win or lose. 2. Trigger restart or return action. | Game returns to the correct state without getting stuck. | Pass | 2026-03-17 | End-state return flow behaved correctly.
BT11 | Start audio | Black-box | Audio | Rendering, UI, and Audio | Audio in start state | 1. Open the game. 2. Interact if required by browser audio policy. | Start music plays when expected and does not duplicate. | Pass | 2026-03-17 | -
BT12 | Audio transitions across screens | Black-box | Audio | Rendering, UI, and Audio | start -> tutorial/intro -> playing -> pause -> ending/credits | 1. Move through each major screen transition; 2. Listen after each transition. | The correct track plays for the active screen, the previous track stops, and no duplicate playback starts. | Pass | 2026-04-17 | -
BT13 | Screen scaling | Boundary Value | Rendering / UI | Rendering, UI, and Audio | Window sizes: small / medium / large | 1. Resize the browser window smaller and larger. | UI scales correctly; important elements remain visible. | Pass | 2026-04-15 | Fixed
BT14 | GitHub Pages deployment | Black-box | Deployment & Launch | Deployment and Platform Behaviour | Execution context: GitHub Pages | 1. Open the deployed version in GitHub Pages. | Game loads correctly; assets, fonts, and audio behave as expected or are documented. | Pass | 2026-04-15 | -
BT15 | GitHub Pages deployment | Black-box | Deployment & Launch | Deployment and Platform Behaviour | hosted deployment | 1. Open the GitHub Pages build; 2. Go from title to gameplay and at least one ending/lose path. | Hosted build loads correctly; assets, fonts, input, and audio behave as expected or limitations are documented. | Pass | 2026-04-16 | -
BT16 | Story-mode entry from Start | Black-box | Start / Mode Selection | Core Game Flow | STORY MODE option | 1. Open Start screen; 2. Select STORY MODE; 3. Press Enter. | The tutorial opens and the story-mode route is prepared for story progression. | Pass | 2026-04-16 | -
BT17 | Standalone tutorial entry from Start | Black-box | Start / Mode Selection | Core Game Flow | TUTORIAL option | 1. Open Start screen; 2. Select TUTORIAL; 3. Press Enter. | The tutorial opens without incorrectly starting the story playthrough flow. | Pass | 2026-04-16 | -
BT18 | Tutorial page navigation | Black-box | Tutorial / Story Flow | Core Game Flow | first page / middle page / last page | 1. Open the tutorial; 2. Use Left and Right arrows across all pages. | Pages move correctly, page order is stable, and the user cannot move past the first or last page. | Pass | 2026-04-16 | -
BT19 | Tutorial completion and skip flow | Black-box | Tutorial / Story Flow | Core Game Flow | last-page Enter / hold E skip | 1. Open the tutorial from story mode; 2. Complete it with Enter on the last page; 3. Repeat using hold E to skip. | Both routes end cleanly at playthrough select with no partial state left behind. | Pass | 2026-04-16 | Fixed
BT20 | Difficulty selection flow | Black-box | Start / Mode Selection | Core Game Flow | choose difficulty / Escape back | 1. From Start choose NORMAL MODE; 2. Move between options; 3. Confirm each option; 4. Repeat and press Escape. | Each selection loads the correct map into gameplay, and Escape returns to the title screen. | Pass | 2026-04-16 | -
BT21 | Pause menu basic actions | Black-box | Pause / Notes | Player Interaction Systems | RESUME / READ NOTES / EXIT TO TITLE | 1. Enter gameplay; 2. Press Escape; 3. Test each pause-menu option. | Resume returns to gameplay, notes view opens, and Exit to Title returns safely to the Start screen. | Pass | 2026-04-16 | -
BT22 | Pause notes empty state | Black-box | Pause / Notes | Player Interaction Systems | no collected notes | 1. Enter gameplay before collecting a note; 2. Open Pause -> READ NOTES. | The empty-notes state is stable, readable, and allows backing out without errors. | Pass | 2026-04-16 | -
BT23 | Pause note reader with collected notes | Black-box | Pause / Notes | Player Interaction Systems | one collected note / multiple collected notes | 1. Collect at least one note; 2. Open Pause -> READ NOTES; 3. Open a note, scroll, and return. | Correct note title/body appear, scrolling works, and Enter/Escape returns to the notes list. | Pass | 2026-04-16 | -
BT24 | Playthrough select lock and unlock | Black-box | Tutorial / Story Flow | Core Game Flow | first playthrough / second locked / second unlocked | 1. Reach PLAYTHROUGH SELECT; 2. Try the locked second option; 3. Unlock it by the intended flow or unlock shortcut; 4. Select both options. | Locked option blocks selection until unlocked; once unlocked, both options route correctly into their intro variants. | Pass | 2026-04-16 | -
BT25 | Second-playthrough intro routing | Black-box | Tutorial / Story Flow | Core Game Flow | introVariant = second | 1. Select second playthrough; 2. Continue through the second intro. | The second intro ends at map select rather than entering gameplay directly. | Pass | 2026-04-15 | -
BT26 | Map select route loading | Black-box | Tutorial / Story Flow | Core Game Flow | LIBRARY / SALON route | 1. Reach MAP SELECT from the second playthrough; 2. Choose each route. | The chosen route loads the correct level and enters gameplay with the expected story route selected. | Pass | 2026-04-15 | -
BT27 | False ending unlock flow | Black-box | Tutorial / Story Flow | Core Game Flow | first story playthrough ending | 1. Complete the first story run; 2. Continue through the false ending. | The false ending sequence completes, second playthrough becomes unlocked, and the game moves to playthrough select. | Pass | 2026-04-16 | -
BT28 | True ending and credits flow | Black-box | Tutorial / Story Flow | Core Game Flow | second story playthrough ending | 1. Complete the second story run; 2. Continue through the true ending; 3. Continue into credits. | The true ending sequence completes, credits open, and Enter from credits returns to title. | Pass | 2026-04-16 | -
BT29 | Chest interaction is one-time only | Black-box | Loot / Inventory | Player Interaction Systems | unopened chest / already opened chest | 1. Open a chest; 2. Attempt to interact with the same chest again. | The first interaction opens the chest and grants loot; repeated interaction does not duplicate loot or reopen logic. | Pass | 2026-04-16 | -
BT30 | Key loot and inventory update | Black-box | Loot / Inventory | Player Interaction Systems | key chest | 1. Open a chest that contains a key; 2. Observe the HUD and inventory; 3. Try the matching door. | Key count updates correctly and the matching locked door becomes unlockable. | Pass | 2026-04-16 | -
BT31 | Note loot and note readability | Black-box | Pause / Notes | Player Interaction Systems | note chest | 1. Open a chest that contains a note; 2. Check HUD note count; 3. Open the pause note viewer. | Note count increases and the new note is available in the reader. | Pass | 2026-04-16 | -
BT32 | Locked door without matching key | Black-box | Doors / Objectives | Player Interaction Systems | locked door / matching key absent | 1. Find a locked door before collecting its key; 2. Interact with it. Recommended manual target: map1 door_4. | The door stays locked and the blocking message explains that the required key is missing. | Pass | 2026-04-16 | -
BT33 | Locked door with matching key | Black-box | Doors / Objectives | Player Interaction Systems | locked door / matching key present | 1. Collect the matching key; 2. Return to the locked door; 3. Interact. | The door unlocks and opens successfully, and the path becomes usable. Also confirm the key is not visibly consumed if that is intended behaviour. | Pass | 2026-04-16 | -
BT34 | Standard door open and close | Black-box | Doors / Objectives | Player Interaction Systems | closed door / open door | 1. Interact with a normal closed door; 2. Interact again when the doorway is clear. | First interaction opens the door, second interaction closes it. | Pass | 2026-04-16 | -
BT35 | Blocked doorway behaviour | Black-box | Doors / Objectives | Player Interaction Systems | doorway clear / doorway blocked | 1. Open a door; 2. Stand in the doorway or let an NPC occupy it; 3. Try to close the door. | The door refuses to close while blocked and reports the blocked-doorway state rather than clipping actors. | Pass | 2026-04-16 | -
BT36 | Light button toggle | Black-box | Rendering / UI | Rendering, UI, and Audio | lit room / dark room | 1. Find a light button; 2. Toggle the room lights off and on. | The room lighting changes, the prompt text updates, and the system remains stable across repeated toggles. | Pass | 2026-04-17 | -
BT37 | Mission unlock after all chests | Black-box | Loot / Inventory | Player Interaction Systems | collected < target / collected = target | 1. Track chest progress; 2. Open the last required chest. | Objective text switches from chest collection to extraction, and extraction becomes unlocked. | Pass | 2026-04-16 | -
BT38 | Extraction prompt and extraction interaction | Black-box | Doors / Objectives | Player Interaction Systems | locked extraction / unlocked extraction | 1. Approach extraction before unlock; 2. Repeat after mission unlock; 3. Interact when in range. | Extraction prompt only appears when unlocked and close enough, and interaction completes the correct level or story outcome. | Pass | 2026-04-16 | Keep separate from normal-mode final-door checks.
BT39 | NPC detection and lose flow | Black-box | NPC / Stealth | Player Interaction Systems | patrol -> detect player -> lose | 1. Enter an NPC vision cone deliberately; 2. Allow detection to complete. | The player is detected, lose flow triggers, and the retry path is available. | Pass | 2026-04-16 | -
BT40 | NPC investigation response | Black-box | NPC / Stealth | Player Interaction Systems | light-change investigation / sprint-footstep investigation | 1. Toggle a room light near an NPC; 2. Sprint within an NPC's awareness range. | NPC behaviour changes from patrol to investigation/search instead of ignoring the stimulus. | Pass | 2026-04-16 | -
BT41 | Sprint and stamina loop | Black-box | Player Controls & Camera | Player Interaction Systems | full stamina / exhausted / recovery | 1. Sprint continuously until stamina drops; 2. Stop moving and wait. | Sprint speed boost works, stamina drains while sprinting, and recovers after the intended delay. | Pass | 2026-04-16 | -
BT42 | Exploration and fog-of-war reveal | Black-box | Rendering / UI | Rendering, UI, and Audio | unexplored room / explored room | 1. Move through multiple rooms; 2. Revisit them. | Newly entered rooms become visible and remain marked explored after the player leaves. | Pass | 2026-04-17 | -
BT43 | Mouse-wheel zoom and camera bounds | Black-box | Player Controls & Camera | Player Interaction Systems | zoom in / zoom out / map edge | 1. Enter gameplay; 2. Use the mouse wheel at centre and near edges. | Camera zoom changes smoothly without losing the player or exposing invalid bounds. | Pass | 2026-04-16 | -
BT44 | Window blur input reset | Black-box | Player Controls & Camera | Player Interaction Systems | held movement input then focus loss | 1. Hold a movement key; 2. Remove window focus; 3. Return to the game. | Input resets safely and the player does not continue moving after focus returns. | Pass | 2026-04-16 | -
BT45 | First portal placement | Black-box | Portal System | Core Game Flow | Valid first placement on walkable tile | 1. Start level 2. Face an open walkable tile 3. Press space once | A single portal appears directly in front of the player. No teleportation occurs yet. | Pass | 2026-04-16 | -
BT46 | Second portal placement | Black-box | Portal System | Core Game Flow | Valid second placement on walkable tile | 1. Place the first portal 2. Move to another valid location 3. Face open ground and press space | A second portal appears at the new location. Both portals remain active. | Pass | 2026-04-16 | -
BT47 | Teleport from portal A to B | Black-box | Portal System | Core Game Flow | Basic teleport path | 1. Place two portals 2. Walk into the first portal | The player is teleported to the second portal's location without getting stuck or crashing. | Pass | 2026-04-16 | -
BT48 | Teleport from portal B to A | Black-box | Portal System | Core Game Flow | Reverse teleport path | 1. Place two portals 2. Walk into the second portal | The player is teleported to the first portal's location without getting stuck or crashing. | Pass | 2026-04-16 | -
BT49 | Oldest portal replacement | Black-box | Portal System | Core Game Flow | Third placement replaces oldest | 1. Place two portals 2. Move to a third valid location 3. Press space again | The oldest portal is replaced by the new portal. Both portals remain active. | Pass | 2026-04-16 | -
BT50 | Invalid portal placement | Black-box | Portal System | Core Game Flow | Blocked tile placement | 1. Face a wall or a blocked tile 2. Press space | No new portal is placed. Any existing portals remain active. Gameplay continues normally. | Pass | 2026-04-16 | -
BT51 | Teleport anti-bounce protection | Black-box | Portal System | Core Game Flow | Immediate re-entry prevention | 1. Place two portals 2. Walk into one portal 3. Remain standing on or near portal | The player does not ping-pong back and forth between portals. | Pass | 2026-04-16 | -
BT52 | Portal state reset on level change | Black-box | Portal System | Core Game Flow | Level transition reset | 1. Place one or two portals 2. Switch levels or load a new map | Portals do not carry over into the new level. | Pass | 2026-04-16 | -
BT53 | Enemy chase interruption on teleport | Black-box | Portal System | Core Game Flow | Chasing enemy interrupted on teleport | 1. Get an enemy to begin chasing the player 2. Teleport through a portal while being chased | The chasing enemy stops pursuing the player after teleport and returns to normal behavior. | Pass | 2026-04-16 | -
BV01 | First Enter press | Boundary Value | Input Handling | Player Interaction Systems | First Enter press | 1. Open the intro. 2. Press Enter once. | It does not skip more than intended on the first press. | Pass | 2026-03-17 | -
BV02 | Very small window | Boundary Value | Rendering / UI | Rendering, UI, and Audio | Very small window | 1. Reduce the browser window a lot. | UI remains usable or the limitation is recorded. | Pass | 2026-04-15 | -
BV03 | Very large window | Boundary Value | Rendering / UI | Rendering, UI, and Audio | Very large window | 1. Maximize the browser window. | Overlays, text, and images keep a sensible layout. | Pass | 2026-04-15 | -
BV04 | Rapid key presses | Boundary Value | Loot / Inventory | Player Interaction Systems | Rapid repeated Enter input | 1. Press Enter repeatedly during transitions. | The flow does not break and states do not skip unexpectedly. | Pass | 2026-03-17 | -
BV05 | Asset loading delay | Boundary Value | Deployment & Launch | Deployment and Platform Behaviour | Initial asset loading | 1. Observe the first seconds after opening the game. | Slow-loading assets do not break the screen; fallbacks work if used. | Pass | 2026-04-15 | Loaded with G4-Slow and disabled cashe. Game does not crash and works correctly
BV06 | Tutorial skip hold threshold | Boundary value | Tutorial / Story Flow | Core Game Flow | hold E for less than 0.8s / at least 0.8s | 1. In story-mode tutorial, hold E just under the threshold; 2. Repeat just over the threshold. | Skip does not trigger too early and does trigger once the threshold is reached. | Pass | 2026-04-15 | -
BV07 | Playthrough unlock hold threshold | Boundary value | Tutorial / Story Flow | Core Game Flow | hold E for less than 1.2s / at least 1.2s | 1. In playthrough select, hold E just under the threshold; 2. Repeat just over the threshold. | Second-playthrough unlock does not trigger too early and does trigger once the threshold is reached. | Pass | 2026-04-15 | -
BV08 | Rapid repeated door input | Boundary value | Doors / Objectives | Player Interaction Systems | spam E around door cooldown | 1. Stand near a door; 2. Press E rapidly several times. | Door state does not flicker or desync, and cooldown prevents invalid rapid toggles. | Pass | 2026-04-16 | -
WT01 | setGameState logic | White-box | Internal Logic | Internal Logic | State transition logic | Call or trace setGameState with valid transitions. | State value changes to the correct target. | Pass | 2026-04-16 | -
WT02 | Screen routing logic | White-box | Internal Logic | Internal Logic | start -> tutorial/difficulty / intro -> playing or map select / ending follow-up | Trace the screen handlers and screen-manager routing for each major branch. | Each branch routes to the expected next screen and does not leave stale state behind. | Pass | 2026-04-16 | -
WT03 | Audio stop/start logic | White-box | Audio | Rendering, UI, and Audio | Audio switch logic | Trigger a state change that switches music. | Previous audio stops before or when new audio starts. | Pass | 2026-04-17 | -
WT04 | Audio track mapping and sync | White-box | Audio | Rendering, UI, and Audio | SCREEN_TRACK_MAP and sync() | Trace track-key resolution and audio sync for major screens. | The resolved track key matches the intended screen mapping, and track switching does not duplicate active playback. | Pass | 2026-04-17 | -
WT05 | Layout helper values | White-box | Internal Logic | Internal Logic | Layout helper outputs | Run layout or scaling helper functions with different sizes. | Returned values are valid and proportional. | Pass | 2026-04-16 | -
WT06 | Overlay draw conditions | White-box | Internal Logic | Internal Logic | Overlay render guard | Trace overlay rendering for different states. | Only the overlay for the active state is drawn. | Pass | 2026-04-17 | -
WT07 | Interaction prompt priority | White-box | Internal Logic | Internal Logic | exit > chest > door > button | Trace getInteractionPrompt() with overlapping nearby interactables. | Prompt priority always resolves to the intended highest-priority interaction. | Pass | 2026-04-17 | -
WT08 | Door state transitions | White-box | Doors / Objectives | Player Interaction Systems | locked / closed / open / forced-open close | Trace unlock(), open(), close(), and cooldown handling. | Door states, solidity, collision tiles, and forced-open behaviour update correctly. | Pass | 2026-04-17 | -
WT09 | Mission unlock and objective text | White-box | Doors / Objectives | Player Interaction Systems | chest progress below target / at target | Trace mission state before and after the final chest is opened. | Objective text, unlocked flag, and extraction prompt state update consistently. | Pass | 2026-04-19 | -
WT10 | Input resolution and reset | White-box | Internal Logic | Internal Logic | last-pressed axis / interact consume / blur reset | Trace InputSystem with opposing directions, interact presses, and reset calls. | Last-pressed direction wins, one-shot actions consume correctly, and reset clears stale input. | Pass | 2026-04-19 | -

## Bugs
Bug ID | Description | Steps to reproduce | Severity | Status | Fix / owner | Open Date | Close Date
B01 | UI scaling fails when browser window is resized. Important elements do not remain visible/aligned. | Open game → resize browser window smaller/larger → observe scaling issue. | High | Closed | Jinni-Li | 2026-03-17 | 2026-04-09
B02 | Pressing E at the end of tutorial in story mode brings to the start page | Open game → Story mode →Tutorial → press E at the end of the tutorial → arrive to the start page | High | Closed | Yan Cui | 2026-04-16 | 2026-04-17